## Sheet1
TASK/SUBTASK |  | RESOURCES |  | 6 April, Wk 6 | [5 empty] | 20 April, Wk 7 | [5 empty] | 27 April, Wk 8 | [5 empty] | 4 May, Wk 9 | [5 empty] | 11 May, Wk 10 | [5 empty] | 18 May, Wk 11 | [5 empty] | 25 May, Wk 12 | [5 empty] | 1 June, Wk 13
No. | Description | Hours | Who | M | T | W | T | F | S/S | M | T | W | T | F | S/S | M | T | W | T | F | S/S | M | T | W | T | F | S/S | M | T | W | T | F | S/S | M | T | W | T | F | S/S | M | T | W | T | F | S/S | M | T | W | T | F | S/S
1 | Basic Planning/Administrative Phase | RESOURCES Hours: 9
1.1 | Compare PIRs and establish design | RESOURCES Hours: 3; RESOURCES Who: Team
1.2 | Establish team roles | RESOURCES Hours: 1; RESOURCES Who: Team
1.3 | Distribute roles to best fit team member | RESOURCES Hours: 1; RESOURCES Who: Team
1.4 | Basic design sketch | RESOURCES Hours: 3; RESOURCES Who: Joseph
1.5 | Allocate budget | RESOURCES Hours: 1; RESOURCES Who: Team
2 | Subsystem Design Phase | RESOURCES Hours: 35
2.1 | Develop WBS for each subsystem | RESOURCES Hours: 2; RESOURCES Who: Team
2.2 | Marking system design | RESOURCES Hours: 9
2.2.1 | Choose marker type | RESOURCES Hours: 2; RESOURCES Who: Joseph
2.2.2 | Rough physical design | RESOURCES Hours: 1; RESOURCES Who: Joseph
2.2.3 | Choose components | RESOURCES Hours: 3; RESOURCES Who: Joseph
2.2.4 | CAD drawing of design | RESOURCES Hours: 3; RESOURCES Who: Joseph
2.3 | Mechanical Design | RESOURCES Hours: 7
2.3.1 | Research provided gearbox | RESOURCES Hours: 1; RESOURCES Who: Abhishekh
2.3.2 | Choose travelling method | RESOURCES Hours: 1; RESOURCES Who: Abhishekh
2.3.3 | Choose appropriate materials for chassis | RESOURCES Hours: 1; RESOURCES Who: Luke
2.3.4 | Design chassis | RESOURCES Hours: 2; RESOURCES Who: Luke
2.3.5 | Choose components and write specification | RESOURCES Hours: 2; RESOURCES Who: Abhishekh
2.4 | Electrical Design | RESOURCES Hours: 5
2.4.1 | Research provided sensors | RESOURCES Hours: 1; RESOURCES Who: Lachlan
2.4.2 | Choose power system | RESOURCES Hours: 1; RESOURCES Who: Abhishekh
2.4.3 | Choose sensors | RESOURCES Hours: 1; RESOURCES Who: Joseph
2.4.4 | Circuit diagram for whole robot | RESOURCES Hours: 2; RESOURCES Who: Luke
2.5 | Software | RESOURCES Hours: 12
2.5.1 | Choose search algorithm | RESOURCES Hours: 2; RESOURCES Who: Lachlan
2.5.2 | Write function to communicate with sensors | RESOURCES Hours: 4; RESOURCES Who: Lachlan
2.5.3 | Choose activation threshold for sensors | RESOURCES Hours: 1; RESOURCES Who: Lachlan
2.5.4 | Write main code | RESOURCES Hours: 5; RESOURCES Who: Lachlan
3 | Subsystem Integration Phase | RESOURCES Hours: 7
3.1 | Bring subsystem designs together | RESOURCES Hours: 7
3.1.1 | Consider component interconnections | RESOURCES Hours: 3; RESOURCES Who: Team
3.1.2 | Modify so that subsystems work together | RESOURCES Hours: 4; RESOURCES Who: Team
4 | Purchasing Phase | RESOURCES Hours: 4
4.1 | Write parts list for whole robot | RESOURCES Hours: 1; RESOURCES Who: Joseph
4.2 | Check all costs are within budget | RESOURCES Hours: 1; RESOURCES Who: Luke
4.3 | Modify component selection if needed | RESOURCES Hours: 2; RESOURCES Who: Team
5 | Build Phase | RESOURCES Hours: 19
5.1 | Develop WBS for build process | RESOURCES Hours: 1; RESOURCES Who: Luke
5.2 | Build as per breakdown | RESOURCES Hours: 10; RESOURCES Who: Team
5.3 | Test components individually | RESOURCES Hours: 5; RESOURCES Who: Team
5.4 | Connect components together | RESOURCES Hours: 3; RESOURCES Who: Team
6 | Testing Phase | RESOURCES Hours: 8
6.1 | Test in environment similar to Demo Day | RESOURCES Hours: 4; RESOURCES Who: Team
6.2 | Modify or redesign as needed | RESOURCES Hours: 4; RESOURCES Who: Team
M | Team Meetings | RESOURCES Hours: 2/wk; 1 June, Wk 13 M: DD; 1 June, Wk 13 T: FR
M | Submission Due | RESOURCES Hours: N/A; 6 April, Wk 6 W: PSP; 4 May, Wk 9 W: MT; 11 May, Wk 10 T: LB
M | Templates | RESOURCES Hours: 1/pt; 6 April, Wk 6 M: F; 20 April, Wk 7 M: G; 20 April, Wk 7 T: H; 27 April, Wk 8 M: I; 27 April, Wk 8 T: J; 4 May, Wk 9 M: K